## Sheet1
Product Backlog
Story | Priority (lower is better) | Effort (higher is more) | Validation
As a user, I want to be able to create a quiz. | 1 | 2 | A new quiz is created.
As a user, I want to be able to add a question to the quiz. | 1 | 2 | A question is added to the quiz.
As a user, I want to be able to have quizzes suggested to me based on topic using keywords. | 4 | 4 | A quiz is suggest to me based on keywords.
As a user, I want to have a unique profile distinct from everyone else. | 2 | 5 | A profile is created with a unique username and password.
As a user, I want a point system and statistics for my profile. | 3 | 4 | The profile that I have created has points allocated to it and an accuracy rating.
As a user, I want to form chat rooms with my classmates | 2 | 3 | A chatroom is formed with other users.
As a user, I want to share a quiz within a chatroom. | 3 | 2 | A quiz appears within the chatroom.
As a user, I want to add image, video, and audio to my quizzes | 3 | 5 | An alternative form of media is added to the created quiz.
As a quiz creator, I want users to be able to report data to me. | 4 | 3 | Data is reported to me.
As a quiz creator, I want to report data to the users. | 4 | 3 | Data is reported to them.
As a user, I want to navigate a fluid User Interface. | 1 | 2 | The UI is reasonably fluid and well organized.
As a quiz creator, I want to be able to mark the correct for my quiz | 1 | 2 | The correct answer is marked so the user knows if the he/she was right or wrong.
As a developer, I want to the quizzes and user information to be stored server-side. | 2 | 5 | If the app is deleted or the phone is factory reset, the data and profile does not dissappear.
As a developer, I want to create a prototype of the UI. | 1 | 3 | The prototype is created to make it easier to implement in Android Studio.